## MAS 90 Day Tracker
TaskName | Phase | Section | FocusArea | TaskDescription | StartDate | DueDate | Status | Notes | LastUpdated
Conduct Anonymous Engagement Survey | Phase 1 | Actions | Diagnose & Benchmark | Conduct a 10-question anonymous engagement survey. | 2026-03-03 | 2026-03-13 |  |  | 2026-03-25
Review last 60 days of QA & Team Metrics | Phase 1 | Actions | Diagnose & Benchmark | Review last 60 days of QA scores, handle times, escalations, and attendance. | 2026-03-03 | 2026-03-13 |  |  | 2026-03-25
Identify Top & Bottom Performers | Phase 1 | Actions | Diagnose & Benchmark | Identify top 20% and bottom 20% performers. | 2026-03-03 | 2026-03-13 |  |  | 2026-03-25
Listen to four calls per rep for baseline | Phase 1 | Actions | Diagnose & Benchmark | Listen to 4 calls per rep to establish a quality baseline. | 2026-03-03 | 2026-03-16 |  |  | 2026-03-25
Meet one-on-one with each team member | Phase 1 | Actions | Diagnose & Benchmark | Meet 1:1 with each team member for 15 minutes to hear their friction points. | 2026-03-03 | 2026-03-16 |  |  | 2026-03-25
Uncover Management Blind Spots | Phase 1 | Outputs | Diagnose & Benchmark | Uncover management blind spots or need for additional support. | 2026-03-03 | 2026-03-13 |  |  | 2026-03-25
Identify individual strengths and weaknesses | Phase 1 | Outputs | Diagnose & Benchmark | Identify individual strengths and weaknesses to tailor training plans accordingly. | 2026-03-03 | 2026-03-13 |  |  | 2026-03-25
Identify cultural blockers | Phase 1 | Outputs | Diagnose & Benchmark | Identify cultural blockers and themes across reps. | 2026-03-03 | 2026-03-13 |  |  | 2026-03-25
Create team charter | Phase 1 | Actions | Reset Expectations & Culture | Create and review a team charter in a team meeting covering professionalism, ownership mindset, call control, clear documentation, and mailbox usage. | 2026-03-09 | 2026-03-16 |  |  | 2026-03-25
Biweekly call calibration spot check | Phase 1 | Manager Routines | Reset Expectations & Culture | Complete biweekly call calibration spot checks in 1:1 meeting. | 2026-03-09 | 2026-03-16 |  |  | 2026-03-25
Maintain daily visibility on floor and virtual channels | Phase 1 | Manager Routines | Reset Expectations & Culture | Maintain daily visibility on the floor and in virtual channels. | 2026-03-09 | 2026-03-16 |  |  | 2026-03-25
Review template response emails from Ops | Phase 1 | Manager Routines | Reset Expectations & Culture | Review template response emails sent from Ops. | 2026-03-10 | 2026-03-16 |  |  | 2026-03-16
Improve QA scores by 10 percent | Phase 1 | Success Metrics | Reset Expectations & Culture | Achieve 10% improvement in QA scores within the first month. | 2026-03-10 | 2026-04-10 |  |  | 2026-03-25
Increase First Call Resolution by 20 percent | Phase 1 | Success Metrics | Reset Expectations & Culture | Achieve 20% increase in First Call Resolution. | 2026-03-10 | 2026-04-10 |  |  | 2026-03-25
Trainings: Professional Presence, Empathy (Conversion Readiness) | Phase 2 | Actions | Rapid Skill Repair | Conduct training on professional presence, empathy, and re-pairing/CFN. | 2026-04-10 | 2026-04-24 |  |  | 2026-03-25
Effective Call Structure (Greeting -> Discovery -> Solution -> Close) | Phase 2 | Actions | Rapid Skill Repair | Train associates on effective call structure from greeting to discovery to solution to close. | 2026-04-10 | 2026-04-24 |  |  | 2026-03-25
Managing Call Control Without Sounding Controlling | Phase 2 | Actions | Rapid Skill Repair | Train and coach associates on managing call control without sounding controlling. | 2026-04-10 | 2026-04-24 |  |  | 2026-03-25
Implement "Two Clarifying Questions" on every call. | Phase 2 | Actions | Rapid Skill Repair | Require associates to ask at least two purposeful information-gathering questions before moving into solutioning. | 2026-04-10 | 2026-04-24 |  |  | 2026-03-25
Demonstrate updated call flow | Phase 2 | Staff Deliverables | Rapid Skill Repair | Staff consistently demonstrate the updated call flow. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Apply tone and professional presence guidelines | Phase 2 | Staff Deliverables | Rapid Skill Repair | Staff apply tone and professional-presence guidelines in all interactions. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Document all calls accurately and uniformly | Phase 2 | Staff Deliverables | Rapid Skill Repair | Staff document all calls accurately and uniformly. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Improve problem diagnosis | Phase 2 | Success Metrics | Rapid Skill Repair | Improve problem diagnosis and reduce repeat contacts. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Improve call flow smoothness | Phase 2 | Success Metrics | Rapid Skill Repair | Improve call flow so the agent leads the conversation smoothly without sounding forceful. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Increase customer confidence | Phase 2 | Success Metrics | Rapid Skill Repair | Improve customer confidence so callers feel they are truly understood. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Improve QA Scores | Phase 2 | Success Metrics | Rapid Skill Repair | Improve QA scores by reducing missed details. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Reduce escalations by 10 percent | Phase 2 | Success Metrics | Rapid Skill Repair | Reduce escalations by 10% by identifying root issues upfront. | 2026-04-10 | 2026-04-30 |  |  | 2026-03-25
Deliver technical product training | Phase 2 | Actions | Technical & Product Mastery | Conduct training on Trade Corrections, Managed Accounts, Manager Select, Model Hub, Portfolio Models, Fixed Income, and Tax Harvest. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Launch scenario simulation labs | Phase 2 | Actions | Technical & Product Mastery | Launch monthly scenario simulation labs using real advisor situations. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Share call snippets for best-course analysis | Phase 2 | Actions | Technical & Product Mastery | Share a snippet of a call so FSPs can determine the best course of action to address the issue. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Publish Performance Tiers | Phase 2 | Actions | Technical & Product Mastery | Publish clear performance tiers consistently visible to staff: Tier 1 - Developing Tier 2 - Consistent Tier 3 - High Performer Tier 4 - SME or Lead Track | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Create improvement plans for bottom 10 percent | Phase 2 | Actions | Technical & Product Mastery | Create improvement plans and supports for the bottom 10% | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Create recognition and perks for top 25 percent | Phase 3 | Actions | Rewards & Recognition | Create recognition and perks for the top 25% | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Weekly Coaching Routine | Phase 2 | Manager Routines | Technical & Product Mastery | Maintain weekly 30-minute coaching sessions. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Track Skill Levels | Phase 2 | Manager Routines | Technical & Product Mastery | Track skill levels throughout the technical and product mastery phase. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Reduce Error Rates by 25 percent | Phase 2 | Success Metrics | Technical & Product Mastery | Achieve a 25% reduction in error rates. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Improve Resolution Speed on common cases by 50 percent | Phase 2 | Success Metrics | Technical & Product Mastery | Achieve 50% faster resolution on common cases. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Improve call handling confidence | Phase 2 | Success Metrics | Technical & Product Mastery | Improve confidence in call handling. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Maintain Consistent Attendance | Phase 2 | Success Metrics | Technical & Product Mastery | Maintain consistent attendance across the team. | 2026-05-01 | 2026-05-31 |  |  | 2026-03-25
Launch Monthly Performance Awards | Phase 3 | Actions | Rewards & Recognition | Launch monthly performance awards program including Advisor Choice Award, Top QA Score, Most Improved, and Professional Excellence Award. | 2026-06-01 | 2026-06-15 |  |  | 2026-03-25
Create a Recognition Environment | Phase 3 | Actions | Rewards & Recognition | Publicly celebrate wins in team meetings & chat channels. Create a rotating Recognition Wall. | 2026-06-01 | 2026-06-30 |  |  | 2026-03-25
Demonstrate mastery in live call evaluations | Phase 3 | Staff Deliverables | Rewards & Recognition | Staff demonstrate mastery in live call evaluations. | 2026-06-01 | 2026-06-30 |  |  | 2026-03-25
Actively contribute to culture and peer support | Phase 3 | Staff Deliverables | Rewards & Recognition | Staff actively contribute to team culture and peer support. | 2026-06-01 | 2026-06-30 |  |  | 2026-03-25
High-Performance Metrics | Phase 3 | Success Metrics | Rewards & Recognition | - High energy, high pride environment. - Advisors noticing improved professionalism. - Improved employee engagement results. | 2026-06-01 | 2026-06-30 |  |  | 2026-03-25